## Summary
Billkaro Windows — QA Test Report
Report Date | 2026-06-07 15:18
Project | billkaro_windows (Billkaro ChillKaro Desktop)
Platform Tested | Windows (Flutter 3.35.2 / Dart 3.9.0)
Build Status | PASS — Release build succeeded (~392.8s)
Automated Tests | billkaro_windows: 0/1 pass. billkaro-app: 14/18 pass (4 compile failures).
Static Analysis | 1441 issues (mostly info/warnings; 2 errors in test file)
Testing Method | Build verification, automated tests, static analysis, customer-journey code review
Findings by Severity
Critical | 5
High | 18
Medium | 27
Low | 10
Findings by Category
Bug | 35
Improvement | 19
Test Gap | 6
Top 10 Priority Fixes
QA-007 — Global SSL certificate bypass | Critical
QA-045 — Default API points to dev tunnel | Critical
QA-046 — Only broken default widget test | Critical
QA-001 — Silent login failure | Critical
QA-036 — Hardcoded dev ngrok URL and phone numbers | Critical
QA-051 — Connectivity check type mismatch | High
QA-031 — Force-unwrap on failed API | High
QA-052 — Missing app_snackbar.dart breaks 4 tests | High
QA-030 — Empty list shows onboarding not list | High
QA-044 — 502 response triggers logout | High

## QA Report
ID | Category | Severity | Module / Feature | Title | Description | Steps to Reproduce | Expected Behavior | Actual Behavior | Suggested Fix | File Path(s) | Status | Priority Rank
QA-001 | Bug | Critical | Login | Silent login failure | Login only navigates when API response is non-null. Catch block only logs to console. | 1. Enter credentials 2. API returns null or throws non-Dio error | Clear error snackbar/dialog shown | Spinner stops; user stays on login with no message | Show showError() when response is null and in catch block | lib\app\modules\Login\login_controller.dart | Open | 2
QA-002 | Bug | High | Login | Weak password validation | Password validator allows minimum 3 characters. | Sign in with 3-character password | Stronger password policy (8+ chars) | Accepts 3-character passwords | Align validation with backend policy | lib\app\modules\Login\login_controller.dart | Open | 15
QA-003 | Bug | High | Login | Misleading validation messages | Validators show email/password errors for registration key / device label fields. | Submit login form with empty fields | Field-specific error labels | Confusing copied validation messages | Rename validators and error strings to match login fields | lib\app\modules\Login\login_controller.dart | Open | 20
QA-004 | Bug | Medium | Login | Login proceeds without outlet | App navigates to home even when outletData is null or empty. | Log in with account that has no outlets configured | Outlet setup prompt or error | Lands in app with no selected outlet | Block navigation and show setup flow when no outlets | lib\app\modules\Login\login_controller.dart | Open | 18
QA-005 | Bug | Medium | Login | Label mismatch: Request registration key | Button says Request registration key but opens Forgot Password flow. | Tap link on login screen | Label matches behavior | Mismatched label and action | Rename to Forgot password? or implement registration key flow | lib\app\modules\Login\login_screen.dart | Open | 25
QA-006 | Bug | Medium | Login | Stub Add Device shows fake success | onAddDevice() simulates delay and shows success without API call. | Submit add-device form if exposed | Real device registration via API | Fake success after 2s delay | Wire to real API or remove/hide feature | lib\app\modules\Login\login_controller.dart | Open | 30
QA-007 | Bug | Critical | Security | Global SSL certificate bypass | MyHttpOverrides accepts all TLS certificates; set globally in main and login. | MITM on public/corporate Wi-Fi | Valid certificate validation | All certificates trusted | Remove bypass in production; use proper certs or pinning | lib\app\services\Network\api_overRides.dart; lib\main.dart; login_controller.dart | Open | 1
QA-008 | Bug | High | Auth / Staff | Staff session flag never enforced | isStaffSession is set on login but never checked elsewhere for RBAC. | Log in as staff; access admin screens | Role-based route/action restrictions | No RBAC enforcement in UI | Gate routes and actions on isStaffSession and permissions | lib\app\modules\Login\login_controller.dart; lib\config\app_pref.dart | Open | 8
QA-009 | Improvement | Low | Splash | Fixed 3-second splash delay | Splash always waits 3 seconds before routing regardless of init speed. | Launch app | Navigate when initialization completes | Artificial 3s wait every launch | Route as soon as auth/prefs are ready | lib\app\modules\splash\splash_controller.dart | Open | 45
QA-010 | Bug | High | Add Order | Generic offline save failure message | Offline branch catch shows generic failed_to_save_order_offline without root cause. | Save order offline when DB write fails | Actionable error with reason | Generic offline failure message only | Log and surface specific failure reason | lib\app\modules\AddOrder\add_order_controller.dart | Open | 14
QA-011 | Improvement | Medium | Add Order / Sync | Offline orders do not trigger immediate sync | Offline save writes to DB but does not call SyncManager.triggerSync() when back online from this flow. | Create offline order; reconnect network | Prompt sync attempt on reconnect | Relies on 15-min timer or connectivity listener only | Trigger sync after successful offline save when online | lib\app\modules\AddOrder\add_order_controller.dart; lib\app\services\sync\sync_manager.dart | Open | 22
QA-012 | Bug | Medium | Add Order / Tables | Dine-in table conflict edge cases offline | Active table order check may desync across offline terminals. | Two terminals offline assign same table | Consistent conflict prevention | Depends on local state freshness | Strengthen offline table locking and conflict UI | lib\app\modules\AddOrder\add_order_controller.dart | Open | 28
QA-013 | Bug | Medium | KOT Preview | Null-force crash on staff/user | getUserDetails() uses appPref.user! and outletData!.first without null checks. | Open KOT preview with incomplete profile or staff session | Graceful fallback names | Possible runtime crash | Null-safe access with fallback values | lib\app\modules\Invoice\KOT\kot_preview_controller.dart | Open | 16
QA-014 | Bug | Medium | KOT Print | KOT PDF export unimplemented | buildPdf() throws UnimplementedError. | Trigger KOT PDF export path | Working PDF or disabled UI | Runtime UnimplementedError | Implement PDF generation or hide/disable action | lib\app\services\printerService.dart\thermal_printer\kot_print.dart | Open | 24
QA-015 | Improvement | Low | Add Order | Order preferences navigation commented out | Order preferences route call is commented out in controller. | Try accessing preferences from add-order flow | Working preferences shortcut | Dead code path | Restore navigation or remove UI entry | lib\app\modules\AddOrder\add_order_controller.dart | Open | 50
QA-016 | Bug | High | Item Reports | Null crash on payment filter | Offline filter uses order.paymentReceivedIn!.toLowerCase() — crashes when null. | Filter Item Reports by payment type with orders missing payment field | Null-safe filter match | Null assertion crash | Use ?.toLowerCase() ?? empty string like order reports | lib\app\modules\Reports\ItemReports\item_reports_controller.dart | Open | 7
QA-017 | Improvement | Medium | Reports | Customer filter not implemented | filterByCustomers() shows coming soon; selectedCustomers filter state unused in UI. | Open reports and look for customer filter | Working customer filter dialog | Stub message; dead backend filter state | Implement dialog or remove filter UI/state | lib\app\modules\Reports\ItemReports\item_reports_controller.dart; OrderReports\order_reports_controller.dart | Open | 32
QA-018 | Bug | Medium | Business Overview | Wrong navigation to Item Reports | Uses Get.toNamed(AppRoute.itemReports) instead of Modular shell route. | From Business Overview empty state tap View Item Reports | Opens item reports inside shell | May push outside Modular context / wrong stack | Use Modular.to.pushNamed(HomeMainRoutes.itemsReport) | lib\app\modules\Reports\BusinessOverview\business_overview_screen.dart | Open | 26
QA-019 | Improvement | Low | Order Reports | PDF preview route commented out | Large block of invoice PDF preview navigation is commented. | Tap invoice action in order reports if visible | PDF preview opens | Incomplete or alternate path only | Finish PDF preview or remove dead code | lib\app\modules\Reports\OrderReports\order_reports_screen.dart | Open | 48
QA-020 | Bug | Medium | Order Reports | Hard null on user ID fetch | API call uses appPref.user!.id! without guard. | Open reports with cleared or corrupt user pref | Error message shown | Possible crash | Guard user/outlet before API calls | lib\app\modules\Reports\OrderReports\order_reports_controller.dart | Open | 21
QA-021 | Bug | High | Tables | Fake default tables on API failure | When API returns empty/fails, _defaultTables() generates 12 local phantom tables. | Open Tables with API down or new outlet | Empty state or error message | 12 invented tables shown (table_1..table_12) | Show error/empty state; do not invent tables | lib\app\modules\Tables\table_controller.dart | Open | 6
QA-022 | Bug | High | Tables | Table free-after-payment incomplete | closeOrderAndFreeTable() DB update is commented out; only calls loadTables(). | Complete payment and free table | Order closed in DB and table available | Table may remain occupied until reload/sync | Restore DB update logic | lib\app\modules\Tables\table_controller.dart | Open | 9
QA-023 | Bug | High | Kitchen Display | Windows defaults to localhost WebSocket | On Windows KDS WS defaults to ws://127.0.0.1:3000 while REST may use remote tunnel URL. | Run KDS on Windows without .env KDS flags against remote backend | WebSocket host matches REST API | WS connects to localhost by default | Default _useLocalKdsWebSocket to false for production builds | lib\app\services\Network\api_config.dart | Open | 11
QA-024 | Bug | Medium | Kitchen Display | KDS disconnect errors swallowed | WebSocket close errors caught with empty catch blocks. | Disconnect during network flap | Surfaced error/reconnect status | Silent failure | Log/show lastError; avoid empty catches | lib\app\services\kds\kds_realtime_service.dart | Open | 33
QA-025 | Bug | Medium | KOT History | Load errors hidden from user | load() / loadMore() catch blocks only debugPrint. | Corrupt DB or load failure in KOT History | User-visible error with retry | Silent empty list | Show error banner and retry button | lib\app\modules\KOTHistory\kot_history_controller.dart | Open | 27
QA-026 | Improvement | Low | Routes | Typo in WhatsApp route constant | Route named whatsaapMarketing (misspelled). | Inspect route names / deep links | Consistent whatsappMarketing naming | Typo persisted in route ID | Rename with migration plan | lib\app\modules\HomeMain\home_main_routes.dart | Open | 52
QA-027 | Bug | Medium | Printer | Bluetooth not supported error on desktop | checkBluetoothPermission() shows error if FlutterBluePlus.isSupported is false. | Open Printer screen on Windows without BT stack | USB-first UX on Windows | Error snackbar even if USB printing works | Gate BT messaging by platform; default to USB tab on Windows | lib\app\modules\Printer\printer_controller.dart | Open | 29
QA-028 | Bug | Medium | Printer | Empty catch blocks hide print failures | Multiple printer helpers swallow exceptions silently. | Print or connect failure | User notified of failure | Silent failure possible | Surface errors to UI snackbar/dialog | lib\app\services\printerService.dart\thermal_printer\thermal_printer_service.dart | Open | 31
QA-029 | Bug | Medium | KOT Print | KOT validation requires waiter name | KotPrintJob.validate() fails if waiterName is empty. | Auto-print KOT when brandName/waiter missing | Print with fallback staff name | Validation failure prevents print | Relax validation or always set fallback name | lib\app\services\printerService.dart\thermal_printer\kot_print.dart | Open | 34
QA-030 | Bug | High | Customers | Empty list shows onboarding not list | customerList.isEmpty renders CustomerTrackingScreen for loading, API failure, and zero customers. | Open Customers before API returns or after API error | Loader then list or proper empty state | Onboarding/marketing screen shown incorrectly | Add loading/error states; distinguish zero customers | lib\app\modules\Regular customer\CustomerList\customer_list_Screen.dart | Open | 5
QA-031 | Bug | High | Customers | Force-unwrap on failed API | Uses response!.status when callApi returns null. | Open customers offline or on API error | Error message shown | Null check operator crash | Use response?.status and error UI | lib\app\modules\Regular customer\CustomerList\cutomer_list_controller.dart | Open | 4
QA-032 | Improvement | Medium | Customers | Typo in controller class name | CutomerListController misspelled throughout module. | N/A (maintainability) | CustomerListController naming | Typo in type and file name | Rename class and file for maintainability | lib\app\modules\Regular customer\CustomerList\cutomer_list_controller.dart | Open | 46
QA-033 | Bug | High | Staff | Wrong permission mapping for Edit menu | UI flag canEditMenuItems maps to permission view_reports not menu edit. | Create biller with Edit menu checked | Menu edit permission granted | Only view_reports granted | Map to correct backend permission key | lib\app\modules\Staff\add_staff_controller.dart | Open | 10
QA-034 | Bug | Medium | Staff | Hydration maps wrong permission to UI | When editing staff, canEditMenuItems set from view_reports permission. | Edit existing staff member | Checkbox reflects menu edit permissions | Mislabeled capability in UI | Fix permission to UI mapping both directions | lib\app\modules\Staff\add_staff_controller.dart | Open | 23
QA-035 | Improvement | Low | Signup | Address save not persisted to backend | AddAddressController.saveAddress() has TODO; only print and local result. | Complete signup address step | Address saved via API | Local-only save | Implement API persistence | lib\app\modules\Signup\address_controller.dart | Open | 49
QA-036 | Bug | Critical | WhatsApp Marketing | Hardcoded dev ngrok URL and phone numbers | Bulk send posts to ngrok URL with hardcoded Indian test numbers. | Send WhatsApp campaign from app | Outlet customer list and production API | Dev tunnel and fixed test numbers used | Load customers from DB/API; configurable endpoint | lib\app\modules\Whatsapp Marketing\whatsapp_marketing_controller.dart | Open | 3
QA-037 | Improvement | Medium | WhatsApp Marketing | Primary bulk-send flow commented out | sendBulkWhatsAppMessages and validation fully commented; ngrok path is active workaround. | Use non-ngrok template send | Production WhatsApp integration | Dead code; ngrok workaround only | Restore/implement official Twilio integration | lib\app\modules\Whatsapp Marketing\whatsapp_marketing_controller.dart | Open | 35
QA-038 | Improvement | Low | Settings / Menu | Language change menu disabled | Language menu item commented out in Menu screen. | Menu → Language | Language settings accessible | Entry removed/commented | Re-enable HomeMainRoutes.changeLanguage | lib\app\modules\Menu\menu_screen.dart | Open | 47
QA-039 | Improvement | Low | Branding | Inconsistent product naming in UI | Window title Billkaro ChillKaro, app title BillKaro, exit dialog double space. | View title bar and exit dialog | Consistent brand string | Mixed spelling and spacing | Standardize branding copy across app | lib\main.dart; lib\app\Widgets\windows_desktop_title_bar.dart; lib\utils\exit_confirm_helper.dart | Open | 51
QA-040 | Improvement | Low | Module naming | OrderPrefrences typo in folder/module | Folder and imports use OrderPrefrences / order_prefrences_*. | N/A (maintainability) | OrderPreferences naming | Typo persisted in paths | Rename module in refactor | lib\app\modules\OrderPrefrences\ | Open | 53
QA-041 | Bug | High | Offline Sync | Only selected outlet pending orders sync | syncPendingOrders filters pending orders to selectedOutletId only. | Save offline orders for outlet A; switch to outlet B; reconnect | All outlets sync or warning shown | Outlet A orders remain pending silently | Sync all pending orders or show cross-outlet pending count | lib\app\services\Synchronisatioin\synchronisation.dart | Open | 12
QA-042 | Bug | Medium | Offline Sync | No Windows sync notifications | SyncNotificationService initializes Android/iOS local notifications only. | Sync pending orders on Windows | In-app sync status indicator | Debug logs only | Add in-app toast/banner on Windows desktop | lib\app\services\sync\sync_notification_service.dart; sync_manager.dart | Open | 36
QA-043 | Bug | High | Offline Sync | 4xx failed orders never retried, no user queue | Client errors logged as will not retry; orders stay pending with no surfaced queue UI. | Sync order rejected by server validation (4xx) | User notified with fix/retry flow | Stuck pending in DB silently | Surface failed sync list; allow edit/delete/retry | lib\app\services\Synchronisatioin\synchronisation.dart | Open | 13
QA-044 | Bug | High | Network / Auth | 502 response triggers logout | On 502 interceptor calls _handleTokenExpiration() clearing all data. | Server returns 502 during normal use | Retry message; stay logged in | Session cleared / forced logout | Treat 502 as transient; do not clear session | lib\app\services\Network\network_module.dart | Open | 5
QA-045 | Bug | Critical | Config | Default API points to dev tunnel | Fallback base URL is devtunnels.ms when .env missing. | Run production build without .env | Production API endpoint | Dev tunnel endpoint used | Require env/config for release; fail fast if unset | lib\app\services\Network\urls.dart; api_config.dart | Open | 1
QA-046 | Test Gap | Critical | Tests | Only broken default widget test | Single test expects counter app and imports billkaro_windows/main.dart while package is billkaro. | Run flutter test in billkaro_windows | Passing suite covering core flows | 0/1 tests pass — compile failure | Replace with real tests; fix import to package:billkaro/main.dart | billkaro_windows\test\widget_test.dart | Open | 1
QA-047 | Test Gap | High | Tests | No auth flow tests | No unit/widget tests for login, staff login, token expiry, splash routing. | Run flutter test | Login success/failure/session tests | Zero coverage | Add controller tests with mocked ApiClient | billkaro_windows\test\ | Open | 17
QA-048 | Test Gap | High | Tests | No order/offline sync tests | No tests for offline order save, pending sync, 4xx handling, outlet filtering. | Run flutter test | Sync integration tests | None exist | Add tests with in-memory DB and mock API | synchronisation.dart; add_order_controller.dart | Open | 19
QA-049 | Test Gap | Medium | Tests | No reports export/filter tests | Excel/PDF export and payment/date filters untested. | Run flutter test | Filter/export regression tests | None exist | Test applyAllFilters() and export helpers | item_reports_controller.dart; order_reports_controller.dart | Open | 37
QA-050 | Test Gap | Medium | Tests | No printer/KDS integration tests | Printer assignment, KOT validation, KDS WS reconnect logic untested. | Run flutter test | Unit tests for critical paths | None exist | Add mocked printer/KDS service tests | printer_controller.dart; kds_realtime_service.dart | Open | 38
QA-051 | Bug | High | Network | Connectivity check type mismatch | NetworkUtils.hasInternetConnection compares List<ConnectivityResult> to ConnectivityResult.none. | Call hasInternetConnection() on device | Correct none-network detection | Connectivity none check may never match; wrong online/offline state | Use result.contains(ConnectivityResult.none) like ConnectivityHelper | lib\utils\connectivity\connectivity_helper.dart | Open | 3
QA-052 | Test Gap | High | billkaro-app | Missing app_snackbar.dart breaks 4 tests | billkaro-app imports utils/app_snackbar.dart which does not exist in that project. | Run flutter test in billkaro-app | All tests compile and pass | 14/18 pass; 4 fail to compile | Copy app_snackbar.dart from billkaro_windows or fix import | billkaro-app\lib\app\services\notification\kitchen_new_order_notification_service.dart | Open | 4
QA-053 | Improvement | Medium | Code Quality | 1441 static analysis issues | Mostly deprecated withOpacity, unnecessary imports, avoid_print; indicates tech debt. | Run flutter analyze | Minimal warnings in CI | 1441 info/warning issues; 2 errors in test file | Enable CI analyze gate; fix critical warnings incrementally | billkaro_windows\lib\ | Open | 39
QA-054 | Improvement | Medium | Dependencies | 107 packages have newer incompatible versions | Many dependencies are behind latest compatible versions per flutter pub outdated. | Run flutter pub outdated | Up-to-date secure dependencies | Many packages behind latest | Plan dependency upgrade sprint with regression testing | billkaro_windows\pubspec.yaml | Open | 40
QA-055 | Improvement | Low | Build | CMake/NuGet warnings during Windows build | Nuget not installed warning; webview_windows CMP0175 policy warning during build. | flutter build windows | Clean build without warnings | Build succeeds but with developer warnings (392.8s) | Install NuGet; update webview_windows CMake policy | build\windows\ | Open | 54
QA-056 | Improvement | Medium | Home / Dashboard | Large home_screen.dart file (1600+ lines) | Monolithic UI file increases bug risk and slows maintenance. | Navigate home dashboard | Modular widget composition | Single large file hard to test and maintain | Extract chart, stats, and order list into separate widgets | lib\app\modules\Home\home_screen.dart | Open | 41
QA-057 | Improvement | Medium | Add Order | add_order_controller.dart is 2600+ lines | God controller mixing UI state, API, sync, KOT, and table logic. | Create/edit order flow | Separated concerns (service layers) | Hard to test; high regression risk | Split into OrderCreationService, BillNumberService, KotPrintCoordinator | lib\app\modules\AddOrder\add_order_controller.dart | Open | 42
QA-058 | Bug | Medium | Keyboard (Windows) | Hardware keyboard state workaround needed | App requires dynamic clearState() workaround for Alt-key stuck after native dialogs. | Open file dialog then press Alt | Normal keyboard state after dialog | Framework assertion without workaround | Track Flutter desktop fix; keep workaround documented | lib\main.dart | Open | 43
QA-059 | Improvement | Low | Workmanager | Background sync not available on Windows | Workmanager skipped on Windows; sync relies on in-app connectivity listener. | Close app with pending offline orders on Windows | Background sync when app closed | Sync only when app is running | Document limitation; consider Windows background task alternative | lib\main.dart; lib\app\services\sync\sync_manager.dart | Open | 44
QA-060 | Improvement | Medium | Customer UX | Limited automated E2E customer journey tests | No integration test simulating login → create order → payment → report export on Windows. | Manual full customer journey | Automated E2E on CI | Manual testing only | Add integration_test package with mocked API | billkaro_windows\test\ | Open | 55