## Summary
Billkaro Windows — QA Report (Updated After Fixes)
Report Date | 2026-06-07 18:37
Report Version | v2 — Post-fix update
Project | billkaro_windows + billkaro-backend
Platform | Windows Desktop (Flutter 3.35.2)
Build Status | PASS — Release build succeeded
Tests (billkaro_windows) | 1/1 pass (smoke test)
Tests (billkaro-app) | 21/25 pass (4 legacy widget tests still failing)
Total Findings | 60
Bugs Fixed | 31 of 35
Bugs Partially Fixed | 2
Bugs Still Open | 2
Backend Changes | Staff login returns permissions; edit_menu in staff DTOs
Status Summary
Fixed | 35
Partial | 2
Open | 23
Deferred | 0
Remaining Open Bugs (verify manually)
QA-012 — Dine-in table conflict edge cases offline | Open
QA-028 — Empty catch blocks hide print failures | Open
QA-043 — 4xx failed orders never retried, no user queue | Partial
QA-058 — Hardware keyboard state workaround needed | Partial
Deployment Checklist
• Set API_BASE_URL in .env to production URL
• Set Twilio credentials for WhatsApp marketing
• Restart backend to apply staff permissions in login response
• Re-save staff with edit_menu permission where needed
• Run flutter build windows and smoke-test login → order → sync

## QA Report
ID | Category | Severity | Module / Feature | Title | Description | Steps to Reproduce | Expected Behavior | Actual Behavior (Before Fix) | Suggested Fix | File Path(s) | Status | Resolution / Fix Applied | Priority Rank
QA-001 | Bug | Critical | Login | Silent login failure | Login only navigates when API response is non-null. Catch block only logs to console. | 1. Enter credentials 2. API returns null or throws non-Dio error | Clear error snackbar/dialog shown | Spinner stops; user stays on login with no message | Show showError() when response is null and in catch block | lib\app\modules\Login\login_controller.dart | Fixed | login_controller: showError on null response and in catch block. | 2
QA-002 | Bug | High | Login | Weak password validation | Password validator allows minimum 3 characters. | Sign in with 3-character password | Stronger password policy (8+ chars) | Accepts 3-character passwords | Align validation with backend policy | lib\app\modules\Login\login_controller.dart | Fixed | Password minimum raised to 8 characters in validateDeviceLabel(). | 15
QA-003 | Bug | High | Login | Misleading validation messages | Validators show email/password errors for registration key / device label fields. | Submit login form with empty fields | Field-specific error labels | Confusing copied validation messages | Rename validators and error strings to match login fields | lib\app\modules\Login\login_controller.dart | Fixed | Validation messages updated to email/password field labels. | 20
QA-004 | Bug | Medium | Login | Login proceeds without outlet | App navigates to home even when outletData is null or empty. | Log in with account that has no outlets configured | Outlet setup prompt or error | Lands in app with no selected outlet | Block navigation and show setup flow when no outlets | lib\app\modules\Login\login_controller.dart | Fixed | Login blocked with error when outletData is empty. | 18
QA-005 | Bug | Medium | Login | Label mismatch: Request registration key | Button says Request registration key but opens Forgot Password flow. | Tap link on login screen | Label matches behavior | Mismatched label and action | Rename to Forgot password? | lib\app\modules\Login\login_screen.dart | Fixed | Login screen link text changed to 'Forgot password?'. | 25
QA-006 | Bug | Medium | Login | Stub Add Device shows fake success | onAddDevice() simulates delay and shows success without API call. | Submit add-device form if exposed | Real device registration via API | Fake success after 2s delay | Wire to real API or remove/hide feature | lib\app\modules\Login\login_controller.dart | Fixed | onAddDevice() no longer fakes success; shows not-available message. | 30
QA-007 | Bug | Critical | Security | Global SSL certificate bypass | MyHttpOverrides accepts all TLS certificates; set globally in main and login. | MITM on public/corporate Wi-Fi | Valid certificate validation | All certificates trusted | Remove bypass in production | lib\app\services\Network\api_overRides.dart; lib\main.dart | Fixed | SSL bypass limited to kDebugMode only (main.dart + api_overRides.dart). | 1
QA-008 | Bug | High | Auth / Staff | Staff session flag never enforced | isStaffSession is set on login but never checked elsewhere for RBAC. | Log in as staff; access admin screens | Role-based route/action restrictions | No RBAC enforcement in UI | Gate routes on isStaffSession and permissions | lib\utils\staff_access.dart; app_shell_sidebar.dart | Fixed | StaffAccess helper, sidebar route guards, staff permissions in login + backend. | 8
QA-009 | Improvement | Low | Splash | Fixed 3-second splash delay | Splash always waits 3 seconds before routing regardless of init speed. | Launch app | Navigate when initialization completes | Artificial 3s wait every launch | Route as soon as auth/prefs are ready | lib\app\modules\splash\splash_controller.dart | Open | Not addressed — splash still uses fixed delay. | 45
QA-010 | Bug | High | Add Order | Generic offline save failure message | Offline branch catch shows generic failed_to_save_order_offline without root cause. | Save order offline when DB write fails | Actionable error with reason | Generic offline failure message only | Log and surface specific failure reason | lib\app\modules\AddOrder\add_order_controller.dart | Fixed | Offline save catch now logs error and shows message with exception detail. | 14
QA-011 | Improvement | Medium | Add Order / Sync | Offline orders do not trigger immediate sync | Offline save writes to DB but does not call SyncManager.triggerSync() when back online from this flow. | Create offline order; reconnect network | Prompt sync attempt on reconnect | Relies on 15-min timer or connectivity listener only | Trigger sync after successful offline save when online | lib\app\modules\AddOrder\add_order_controller.dart; sync_manager.dart | Fixed | SyncManager.triggerSync(immediate: true) after offline save when online. | 22
QA-012 | Bug | Medium | Add Order / Tables | Dine-in table conflict edge cases offline | Active table order check may desync across offline terminals. | Two terminals offline assign same table | Consistent conflict prevention | Depends on local state freshness | Strengthen offline table locking and conflict UI | lib\app\modules\AddOrder\add_order_controller.dart | Open | Not addressed — offline multi-terminal table locking still needs work. | 28
QA-013 | Bug | Medium | KOT Preview | Null-force crash on staff/user | getUserDetails() uses appPref.user! and outletData!.first without null checks. | Open KOT preview with incomplete profile | Graceful fallback names | Possible runtime crash | Null-safe access with fallback values | lib\app\modules\Invoice\KOT\kot_preview_controller.dart | Fixed | kot_preview_controller getUserDetails() made null-safe with fallbacks. | 16
QA-014 | Bug | Medium | KOT Print | KOT PDF export unimplemented | buildPdf() throws UnimplementedError. | Trigger KOT PDF export path | Working PDF or disabled UI | Runtime UnimplementedError | Implement PDF generation | lib\app\services\printerService.dart\thermal_printer\Print\kot_print.dart | Fixed | KotPrintJob.buildPdf() implemented with basic KOT PDF layout. | 24
QA-015 | Improvement | Low | Add Order | Order preferences navigation commented out | Order preferences route call is commented out in controller. | Try accessing preferences from add-order flow | Working preferences shortcut | Dead code path | Restore navigation or remove UI entry | lib\app\modules\AddOrder\add_order_controller.dart | Open | Order preferences navigation still commented out. | 50
QA-016 | Bug | High | Item Reports | Null crash on payment filter | Offline filter uses order.paymentReceivedIn!.toLowerCase() — crashes when null. | Filter Item Reports by payment type with null payment field | Null-safe filter match | Null assertion crash | Use ?.toLowerCase() null-safe check | lib\app\modules\Reports\ItemReports\item_reports_controller.dart | Fixed | Item reports payment filter uses ?.toLowerCase() null-safe check. | 7
QA-017 | Improvement | Medium | Reports | Customer filter not implemented | filterByCustomers() shows coming soon; selectedCustomers filter state unused in UI. | Open reports and look for customer filter | Working customer filter dialog | Stub message; dead backend filter state | Implement dialog or remove filter UI/state | lib\app\modules\Reports\ItemReports\item_reports_controller.dart | Open | Customer filter in reports still not implemented. | 32
QA-018 | Bug | Medium | Business Overview | Wrong navigation to Item Reports | Uses Get.toNamed(AppRoute.itemReports) instead of Modular shell route. | From Business Overview tap View Item Reports | Opens item reports inside shell | May push outside Modular context | Use Modular.to.navigate(HomeMainRoutes.itemsReport) | lib\app\modules\BusinessOverview\business_overview_screen.dart | Fixed | Business overview uses Modular.to.navigate(HomeMainRoutes.itemsReport). | 26
QA-019 | Improvement | Low | Order Reports | PDF preview route commented out | Large block of invoice PDF preview navigation is commented. | Tap invoice action in order reports if visible | PDF preview opens | Incomplete path only | Finish PDF preview or remove dead code | lib\app\modules\Reports\OrderReports\order_reports_screen.dart | Open | Order reports PDF preview route still commented. | 48
QA-020 | Bug | Medium | Order Reports | Hard null on user ID fetch | API call uses appPref.user!.id! without guard. | Open reports with cleared user pref | Error message shown | Possible crash | Guard user/outlet before API calls | lib\app\modules\Reports\OrderReports\order_reports_controller.dart | Fixed | Order reports guards userId/outletId before API call. | 21
QA-021 | Bug | High | Tables | Fake default tables on API failure | When API fails, _defaultTables() generates 12 local phantom tables. | Open Tables with API down | Empty state or error message | 12 invented tables shown | Show error/empty state; do not invent tables | lib\app\modules\Tables\table_controller.dart | Fixed | Removed fake _defaultTables(); shows empty/error state instead. | 6
QA-022 | Bug | High | Tables | Table free-after-payment incomplete | closeOrderAndFreeTable() DB update was commented out. | Complete payment and free table | Order closed in DB and table available | Table may remain occupied | Restore DB update logic | lib\app\modules\Tables\table_controller.dart | Fixed | closeOrderAndFreeTable() updates local DB via updateOrderStatus(). | 9
QA-023 | Bug | High | Kitchen Display | Windows defaults to localhost WebSocket | KDS WS defaulted to ws://127.0.0.1:3000 while REST used remote URL. | Run KDS on Windows without .env | WebSocket host matches REST API | WS connects to localhost | Default local WS to false; opt-in via .env | lib\app\services\Network\api_config.dart | Fixed | KDS WebSocket defaults to REST host; local WS opt-in via .env only. | 11
QA-024 | Bug | Medium | Kitchen Display | KDS disconnect errors swallowed | WebSocket close errors caught with empty catch blocks. | Disconnect during network flap | Surfaced error/reconnect status | Silent failure | Log errors; avoid empty catches | lib\app\services\kds\kds_realtime_service.dart | Fixed | KDS disconnect errors logged instead of empty catch blocks. | 33
QA-025 | Bug | Medium | KOT History | Load errors hidden from user | load() / loadMore() catch blocks only debugPrint. | Corrupt DB or load failure | User-visible error with retry | Silent empty list | Show error banner and retry | lib\app\modules\KOTHistory\kot_history_controller.dart | Fixed | KOT history loadError shown; loadMore shows snackbar on failure. | 27
QA-026 | Improvement | Low | Routes | Typo in WhatsApp route constant | Route named whatsaapMarketing (misspelled). | Inspect route names | Consistent whatsappMarketing naming | Typo persisted in route ID | Rename with migration plan | lib\app\modules\HomeMain\home_main_routes.dart | Open | Route typo whatsaapMarketing unchanged (breaking change if renamed). | 52
QA-027 | Bug | Medium | Printer | Bluetooth not supported error on desktop | checkBluetoothPermission() shows error if BT unsupported. | Open Printer on Windows | USB-first UX on Windows | Error snackbar even if USB works | Gate BT by platform; USB default tab | lib\app\modules\Printer\printer_controller.dart | Fixed | Windows printer skips BT error; defaults to USB tab on launch. | 29
QA-028 | Bug | Medium | Printer | Empty catch blocks hide print failures | Multiple printer helpers swallow exceptions silently. | Print or connect failure | User notified of failure | Silent failure possible | Surface errors to UI | lib\app\services\printerService.dart\thermal_printer\thermal_printer_service.dart | Open | Some printer empty catch blocks remain in thermal_printer_service. | 31
QA-029 | Bug | Medium | KOT Print | KOT validation requires waiter name | KotPrintJob.validate() fails if waiterName is empty. | Auto-print KOT when waiter missing | Print with fallback staff name | Validation failure prevents print | Relax validation | lib\app\services\printerService.dart\thermal_printer\Print\kot_print.dart | Fixed | KOT validate() no longer requires waiterName; PDF uses Staff fallback. | 34
QA-030 | Bug | High | Customers | Empty list shows onboarding not list | customerList.isEmpty renders onboarding for loading/error/zero customers. | Open Customers before API returns or after error | Loader then list or empty state | Onboarding shown incorrectly | Add loading/error states | lib\app\modules\Regular customer\CustomerList\customer_list_Screen.dart | Fixed | Customer list: loading, error/retry, and empty states separated. | 5
QA-031 | Bug | High | Customers | Force-unwrap on failed API | Uses response!.status when callApi returns null. | Open customers offline | Error message shown | Null check operator crash | Use response?.status and error UI | lib\app\modules\Regular customer\CustomerList\cutomer_list_controller.dart | Fixed | Customer API uses response?.status; no force-unwrap crash. | 4
QA-032 | Improvement | Medium | Customers | Typo in controller class name | CutomerListController misspelled throughout module. | N/A | CustomerListController naming | Typo in type and file name | Rename class and file | lib\app\modules\Regular customer\CustomerList\cutomer_list_controller.dart | Open | CutomerListController typo not renamed (refactor deferred). | 46
QA-033 | Bug | High | Staff | Wrong permission mapping for Edit menu | canEditMenuItems mapped to view_reports not menu edit. | Create biller with Edit menu checked | Menu edit permission granted | Only view_reports granted | Map to edit_menu permission | lib\app\modules\Staff\add_staff_controller.dart; billkaro-backend outlet-staff DTOs | Fixed | Edit menu maps to edit_menu permission; backend DTO updated. | 10
QA-034 | Bug | Medium | Staff | Hydration maps wrong permission to UI | When editing staff, canEditMenuItems set from view_reports. | Edit existing staff | Checkbox reflects menu edit permissions | Mislabeled capability | Fix permission mapping | lib\app\modules\Staff\add_staff_controller.dart | Fixed | Staff edit hydration reads edit_menu permission for checkbox. | 23
QA-035 | Improvement | Low | Signup | Address save not persisted to backend | AddAddressController.saveAddress() has TODO. | Complete signup address step | Address saved via API | Local-only save | Implement API persistence | lib\app\modules\Signup\address_controller.dart | Open | Signup address save still local-only. | 49
QA-036 | Bug | Critical | WhatsApp Marketing | Hardcoded dev ngrok URL and phone numbers | Bulk send used ngrok URL with hardcoded test numbers. | Send WhatsApp campaign | Outlet customer list and Twilio | Dev tunnel and fixed numbers used | Use Twilio + customer API | lib\app\modules\Whatsapp Marketing\whatsapp_marketing_controller.dart | Fixed | WhatsApp uses Twilio + outlet customer list; ngrok/hardcoded numbers removed. | 3
QA-037 | Improvement | Medium | WhatsApp Marketing | Primary bulk-send flow commented out | sendBulkWhatsAppMessages fully commented; ngrok workaround active. | Use Twilio template send | Production WhatsApp integration | Dead code; ngrok only | Restore Twilio integration | lib\app\modules\Whatsapp Marketing\whatsapp_marketing_controller.dart | Fixed | sendBulkWhatsAppMessages() restored with Twilio integration. | 35
QA-038 | Improvement | Low | Settings / Menu | Language change menu disabled | Language menu item commented out in Menu screen. | Menu → Language | Language settings accessible | Entry removed | Re-enable changeLanguage route | lib\app\modules\Menu\menu_screen.dart | Open | Language menu entry still commented out. | 47
QA-039 | Improvement | Low | Branding | Inconsistent product naming in UI | Mixed Billkaro / BillKaro / ChillKaro spelling in titles. | View title bar and exit dialog | Consistent brand string | Mixed spelling | Standardize branding copy | lib\main.dart; windows_desktop_title_bar.dart | Open | Branding strings not standardized. | 51
QA-040 | Improvement | Low | Module naming | OrderPrefrences typo in folder/module | Folder uses OrderPrefrences spelling. | N/A | OrderPreferences naming | Typo in paths | Rename module in refactor | lib\app\modules\OrderPrefrences\ | Open | OrderPrefrences folder typo not renamed. | 53
QA-041 | Bug | High | Offline Sync | Only selected outlet pending orders sync | syncPendingOrders filtered to selectedOutletId only. | Save offline for outlet A; switch to B | All outlets sync or warning | Other outlet orders stuck pending | Sync all pending orders | lib\app\services\Synchronisatioin\synchronisation.dart | Fixed | syncPendingOrders syncs all pending orders, not selected outlet only. | 12
QA-042 | Bug | Medium | Offline Sync | No Windows sync notifications | SyncNotificationService Android/iOS only. | Sync on Windows | In-app sync status indicator | Debug logs only | Windows snackbar fallback | lib\app\services\notification\sync_notification_service.dart | Fixed | Windows sync uses in-app showSuccess/showError snackbars. | 36
QA-043 | Bug | High | Offline Sync | 4xx failed orders never retried, no user queue | 4xx orders logged as will not retry; no queue UI. | Sync order rejected (4xx) | User notified with fix/retry flow | Stuck pending silently | Mark failed + notify user | lib\app\services\Synchronisatioin\synchronisation.dart; app_database.dart | Partial | 4xx orders marked failed in DB + user notified; retry queue UI not built. | 13
QA-044 | Bug | High | Network / Auth | 502 response triggers logout | 502 interceptor called _handleTokenExpiration(). | Server returns 502 | Retry message; stay logged in | Session cleared | Treat 502 as transient | lib\app\services\Network\network_module.dart | Fixed | 502 no longer calls _handleTokenExpiration(); shows retry message. | 5
QA-045 | Bug | Critical | Config | Default API points to dev tunnel | Fallback base URL was devtunnels.ms when .env missing. | Run without .env | Production API endpoint | Dev tunnel used | Default to production API URL | lib\app\services\Network\urls.dart; api_config.dart | Fixed | Default API URL set to production; ApiConstants.defaultBase = prod. | 1
QA-046 | Test Gap | Critical | Tests | Broken default widget test | Test imported wrong package and expected counter app. | Run flutter test | Passing smoke test | 0/1 compile failure | Fix test import and expectations | billkaro_windows\test\widget_test.dart | Fixed | billkaro_windows widget test replaced; 1/1 smoke test passes. | 1
QA-047 | Test Gap | High | Tests | No auth flow tests | No unit tests for login, staff login, token expiry. | Run flutter test | Login success/failure tests | Zero coverage | Add controller tests with mock ApiClient | billkaro_windows\test\ | Open | Auth flow unit tests not added beyond smoke test. | 17
QA-048 | Test Gap | High | Tests | No order/offline sync tests | No tests for offline save, pending sync, 4xx handling. | Run flutter test | Sync integration tests | None exist | Add in-memory DB + mock API tests | synchronisation.dart; add_order_controller.dart | Open | Offline sync integration tests not added. | 19
QA-049 | Test Gap | Medium | Tests | No reports export/filter tests | Excel/PDF export and filters untested. | Run flutter test | Filter/export regression tests | None exist | Test applyAllFilters() and exports | item_reports_controller.dart; order_reports_controller.dart | Open | Reports export/filter tests not added. | 37
QA-050 | Test Gap | Medium | Tests | No printer/KDS integration tests | Printer assignment, KOT validation, KDS reconnect untested. | Run flutter test | Unit tests for critical paths | None exist | Add mocked service tests | printer_controller.dart; kds_realtime_service.dart | Open | Printer/KDS unit tests not added. | 38
QA-051 | Bug | High | Network | Connectivity check type mismatch | Compared List<ConnectivityResult> to ConnectivityResult.none. | Call hasInternetConnection() | Correct none-network detection | Wrong online/offline state | Use result.contains(none) | lib\utils\connectivity\connectivity_helper.dart | Fixed | NetworkUtils uses result.contains(ConnectivityResult.none). | 3
QA-052 | Test Gap | High | billkaro-app | Missing app_snackbar.dart breaks tests | billkaro-app missing utils/app_snackbar.dart. | Run flutter test in billkaro-app | All tests compile | 4 compile failures | Copy app_snackbar.dart from billkaro_windows | billkaro-app\lib\utils\app_snackbar.dart | Fixed | app_snackbar.dart copied to billkaro-app; compile errors resolved. | 4
QA-053 | Improvement | Medium | Code Quality | 1441 static analysis issues | Mostly deprecated withOpacity and unnecessary imports. | Run flutter analyze | Minimal warnings in CI | ~1400 info/warning items | Enable CI analyze gate incrementally | billkaro_windows\lib\ | Open | Static analysis warnings remain (~1400 info items). | 39
QA-054 | Improvement | Medium | Dependencies | 107 packages outdated | Many packages behind latest per flutter pub outdated. | Run flutter pub outdated | Up-to-date dependencies | Many packages behind | Plan upgrade sprint | billkaro_windows\pubspec.yaml | Open | Dependency upgrades not performed. | 40
QA-055 | Improvement | Low | Build | CMake/NuGet warnings during Windows build | Nuget not installed; webview_windows CMP0175 warning. | flutter build windows | Clean build without warnings | Build succeeds with warnings | Install NuGet; update CMake | build\windows\ | Open | CMake/NuGet build warnings remain. | 54
QA-056 | Improvement | Medium | Home / Dashboard | Large home_screen.dart file | Monolithic UI file 1600+ lines. | Navigate home dashboard | Modular widget composition | Hard to maintain | Extract widgets | lib\app\modules\Home\home_screen.dart | Open | home_screen.dart not refactored. | 41
QA-057 | Improvement | Medium | Add Order | add_order_controller.dart 2600+ lines | God controller mixing many concerns. | Create/edit order flow | Separated service layers | High regression risk | Split into services | lib\app\modules\AddOrder\add_order_controller.dart | Open | add_order_controller.dart not split into services. | 42
QA-058 | Bug | Medium | Keyboard (Windows) | Hardware keyboard state workaround needed | clearState() workaround for Alt-key stuck after native dialogs. | Open file dialog then Alt | Normal keyboard state | Framework assertion without workaround | Keep workaround; track Flutter fix | lib\main.dart | Partial | Keyboard workaround retained in main.dart; upstream Flutter issue. | 43
QA-059 | Improvement | Low | Workmanager | Background sync not available on Windows | Workmanager skipped on Windows. | Close app with pending offline orders | Background sync when closed | Sync only when app running | Document limitation | lib\main.dart; sync_manager.dart | Open | Windows background sync via Workmanager still unavailable. | 44
QA-060 | Improvement | Medium | Customer UX | Limited automated E2E tests | No integration test for full customer journey. | Manual full journey | Automated E2E on CI | Manual testing only | Add integration_test package | billkaro_windows\test\ | Open | Full E2E customer journey tests not added. | 55

## Fixed Items
ID | Category | Severity | Module / Feature | Title | Description | Steps to Reproduce | Expected Behavior | Actual Behavior (Before Fix) | Suggested Fix | File Path(s) | Status | Resolution / Fix Applied | Priority Rank
QA-001 | Bug | Critical | Login | Silent login failure | Login only navigates when API response is non-null. Catch block only logs to console. | 1. Enter credentials 2. API returns null or throws non-Dio error | Clear error snackbar/dialog shown | Spinner stops; user stays on login with no message | Show showError() when response is null and in catch block | lib\app\modules\Login\login_controller.dart | Fixed | login_controller: showError on null response and in catch block. | 2
QA-002 | Bug | High | Login | Weak password validation | Password validator allows minimum 3 characters. | Sign in with 3-character password | Stronger password policy (8+ chars) | Accepts 3-character passwords | Align validation with backend policy | lib\app\modules\Login\login_controller.dart | Fixed | Password minimum raised to 8 characters in validateDeviceLabel(). | 15
QA-003 | Bug | High | Login | Misleading validation messages | Validators show email/password errors for registration key / device label fields. | Submit login form with empty fields | Field-specific error labels | Confusing copied validation messages | Rename validators and error strings to match login fields | lib\app\modules\Login\login_controller.dart | Fixed | Validation messages updated to email/password field labels. | 20
QA-004 | Bug | Medium | Login | Login proceeds without outlet | App navigates to home even when outletData is null or empty. | Log in with account that has no outlets configured | Outlet setup prompt or error | Lands in app with no selected outlet | Block navigation and show setup flow when no outlets | lib\app\modules\Login\login_controller.dart | Fixed | Login blocked with error when outletData is empty. | 18
QA-005 | Bug | Medium | Login | Label mismatch: Request registration key | Button says Request registration key but opens Forgot Password flow. | Tap link on login screen | Label matches behavior | Mismatched label and action | Rename to Forgot password? | lib\app\modules\Login\login_screen.dart | Fixed | Login screen link text changed to 'Forgot password?'. | 25
QA-006 | Bug | Medium | Login | Stub Add Device shows fake success | onAddDevice() simulates delay and shows success without API call. | Submit add-device form if exposed | Real device registration via API | Fake success after 2s delay | Wire to real API or remove/hide feature | lib\app\modules\Login\login_controller.dart | Fixed | onAddDevice() no longer fakes success; shows not-available message. | 30
QA-007 | Bug | Critical | Security | Global SSL certificate bypass | MyHttpOverrides accepts all TLS certificates; set globally in main and login. | MITM on public/corporate Wi-Fi | Valid certificate validation | All certificates trusted | Remove bypass in production | lib\app\services\Network\api_overRides.dart; lib\main.dart | Fixed | SSL bypass limited to kDebugMode only (main.dart + api_overRides.dart). | 1
QA-008 | Bug | High | Auth / Staff | Staff session flag never enforced | isStaffSession is set on login but never checked elsewhere for RBAC. | Log in as staff; access admin screens | Role-based route/action restrictions | No RBAC enforcement in UI | Gate routes on isStaffSession and permissions | lib\utils\staff_access.dart; app_shell_sidebar.dart | Fixed | StaffAccess helper, sidebar route guards, staff permissions in login + backend. | 8
QA-010 | Bug | High | Add Order | Generic offline save failure message | Offline branch catch shows generic failed_to_save_order_offline without root cause. | Save order offline when DB write fails | Actionable error with reason | Generic offline failure message only | Log and surface specific failure reason | lib\app\modules\AddOrder\add_order_controller.dart | Fixed | Offline save catch now logs error and shows message with exception detail. | 14
QA-011 | Improvement | Medium | Add Order / Sync | Offline orders do not trigger immediate sync | Offline save writes to DB but does not call SyncManager.triggerSync() when back online from this flow. | Create offline order; reconnect network | Prompt sync attempt on reconnect | Relies on 15-min timer or connectivity listener only | Trigger sync after successful offline save when online | lib\app\modules\AddOrder\add_order_controller.dart; sync_manager.dart | Fixed | SyncManager.triggerSync(immediate: true) after offline save when online. | 22
QA-013 | Bug | Medium | KOT Preview | Null-force crash on staff/user | getUserDetails() uses appPref.user! and outletData!.first without null checks. | Open KOT preview with incomplete profile | Graceful fallback names | Possible runtime crash | Null-safe access with fallback values | lib\app\modules\Invoice\KOT\kot_preview_controller.dart | Fixed | kot_preview_controller getUserDetails() made null-safe with fallbacks. | 16
QA-014 | Bug | Medium | KOT Print | KOT PDF export unimplemented | buildPdf() throws UnimplementedError. | Trigger KOT PDF export path | Working PDF or disabled UI | Runtime UnimplementedError | Implement PDF generation | lib\app\services\printerService.dart\thermal_printer\Print\kot_print.dart | Fixed | KotPrintJob.buildPdf() implemented with basic KOT PDF layout. | 24
QA-016 | Bug | High | Item Reports | Null crash on payment filter | Offline filter uses order.paymentReceivedIn!.toLowerCase() — crashes when null. | Filter Item Reports by payment type with null payment field | Null-safe filter match | Null assertion crash | Use ?.toLowerCase() null-safe check | lib\app\modules\Reports\ItemReports\item_reports_controller.dart | Fixed | Item reports payment filter uses ?.toLowerCase() null-safe check. | 7
QA-018 | Bug | Medium | Business Overview | Wrong navigation to Item Reports | Uses Get.toNamed(AppRoute.itemReports) instead of Modular shell route. | From Business Overview tap View Item Reports | Opens item reports inside shell | May push outside Modular context | Use Modular.to.navigate(HomeMainRoutes.itemsReport) | lib\app\modules\BusinessOverview\business_overview_screen.dart | Fixed | Business overview uses Modular.to.navigate(HomeMainRoutes.itemsReport). | 26
QA-020 | Bug | Medium | Order Reports | Hard null on user ID fetch | API call uses appPref.user!.id! without guard. | Open reports with cleared user pref | Error message shown | Possible crash | Guard user/outlet before API calls | lib\app\modules\Reports\OrderReports\order_reports_controller.dart | Fixed | Order reports guards userId/outletId before API call. | 21
QA-021 | Bug | High | Tables | Fake default tables on API failure | When API fails, _defaultTables() generates 12 local phantom tables. | Open Tables with API down | Empty state or error message | 12 invented tables shown | Show error/empty state; do not invent tables | lib\app\modules\Tables\table_controller.dart | Fixed | Removed fake _defaultTables(); shows empty/error state instead. | 6
QA-022 | Bug | High | Tables | Table free-after-payment incomplete | closeOrderAndFreeTable() DB update was commented out. | Complete payment and free table | Order closed in DB and table available | Table may remain occupied | Restore DB update logic | lib\app\modules\Tables\table_controller.dart | Fixed | closeOrderAndFreeTable() updates local DB via updateOrderStatus(). | 9
QA-023 | Bug | High | Kitchen Display | Windows defaults to localhost WebSocket | KDS WS defaulted to ws://127.0.0.1:3000 while REST used remote URL. | Run KDS on Windows without .env | WebSocket host matches REST API | WS connects to localhost | Default local WS to false; opt-in via .env | lib\app\services\Network\api_config.dart | Fixed | KDS WebSocket defaults to REST host; local WS opt-in via .env only. | 11
QA-024 | Bug | Medium | Kitchen Display | KDS disconnect errors swallowed | WebSocket close errors caught with empty catch blocks. | Disconnect during network flap | Surfaced error/reconnect status | Silent failure | Log errors; avoid empty catches | lib\app\services\kds\kds_realtime_service.dart | Fixed | KDS disconnect errors logged instead of empty catch blocks. | 33
QA-025 | Bug | Medium | KOT History | Load errors hidden from user | load() / loadMore() catch blocks only debugPrint. | Corrupt DB or load failure | User-visible error with retry | Silent empty list | Show error banner and retry | lib\app\modules\KOTHistory\kot_history_controller.dart | Fixed | KOT history loadError shown; loadMore shows snackbar on failure. | 27
QA-027 | Bug | Medium | Printer | Bluetooth not supported error on desktop | checkBluetoothPermission() shows error if BT unsupported. | Open Printer on Windows | USB-first UX on Windows | Error snackbar even if USB works | Gate BT by platform; USB default tab | lib\app\modules\Printer\printer_controller.dart | Fixed | Windows printer skips BT error; defaults to USB tab on launch. | 29
QA-029 | Bug | Medium | KOT Print | KOT validation requires waiter name | KotPrintJob.validate() fails if waiterName is empty. | Auto-print KOT when waiter missing | Print with fallback staff name | Validation failure prevents print | Relax validation | lib\app\services\printerService.dart\thermal_printer\Print\kot_print.dart | Fixed | KOT validate() no longer requires waiterName; PDF uses Staff fallback. | 34
QA-030 | Bug | High | Customers | Empty list shows onboarding not list | customerList.isEmpty renders onboarding for loading/error/zero customers. | Open Customers before API returns or after error | Loader then list or empty state | Onboarding shown incorrectly | Add loading/error states | lib\app\modules\Regular customer\CustomerList\customer_list_Screen.dart | Fixed | Customer list: loading, error/retry, and empty states separated. | 5
QA-031 | Bug | High | Customers | Force-unwrap on failed API | Uses response!.status when callApi returns null. | Open customers offline | Error message shown | Null check operator crash | Use response?.status and error UI | lib\app\modules\Regular customer\CustomerList\cutomer_list_controller.dart | Fixed | Customer API uses response?.status; no force-unwrap crash. | 4
QA-033 | Bug | High | Staff | Wrong permission mapping for Edit menu | canEditMenuItems mapped to view_reports not menu edit. | Create biller with Edit menu checked | Menu edit permission granted | Only view_reports granted | Map to edit_menu permission | lib\app\modules\Staff\add_staff_controller.dart; billkaro-backend outlet-staff DTOs | Fixed | Edit menu maps to edit_menu permission; backend DTO updated. | 10
QA-034 | Bug | Medium | Staff | Hydration maps wrong permission to UI | When editing staff, canEditMenuItems set from view_reports. | Edit existing staff | Checkbox reflects menu edit permissions | Mislabeled capability | Fix permission mapping | lib\app\modules\Staff\add_staff_controller.dart | Fixed | Staff edit hydration reads edit_menu permission for checkbox. | 23
QA-036 | Bug | Critical | WhatsApp Marketing | Hardcoded dev ngrok URL and phone numbers | Bulk send used ngrok URL with hardcoded test numbers. | Send WhatsApp campaign | Outlet customer list and Twilio | Dev tunnel and fixed numbers used | Use Twilio + customer API | lib\app\modules\Whatsapp Marketing\whatsapp_marketing_controller.dart | Fixed | WhatsApp uses Twilio + outlet customer list; ngrok/hardcoded numbers removed. | 3
QA-037 | Improvement | Medium | WhatsApp Marketing | Primary bulk-send flow commented out | sendBulkWhatsAppMessages fully commented; ngrok workaround active. | Use Twilio template send | Production WhatsApp integration | Dead code; ngrok only | Restore Twilio integration | lib\app\modules\Whatsapp Marketing\whatsapp_marketing_controller.dart | Fixed | sendBulkWhatsAppMessages() restored with Twilio integration. | 35
QA-041 | Bug | High | Offline Sync | Only selected outlet pending orders sync | syncPendingOrders filtered to selectedOutletId only. | Save offline for outlet A; switch to B | All outlets sync or warning | Other outlet orders stuck pending | Sync all pending orders | lib\app\services\Synchronisatioin\synchronisation.dart | Fixed | syncPendingOrders syncs all pending orders, not selected outlet only. | 12
QA-042 | Bug | Medium | Offline Sync | No Windows sync notifications | SyncNotificationService Android/iOS only. | Sync on Windows | In-app sync status indicator | Debug logs only | Windows snackbar fallback | lib\app\services\notification\sync_notification_service.dart | Fixed | Windows sync uses in-app showSuccess/showError snackbars. | 36
QA-044 | Bug | High | Network / Auth | 502 response triggers logout | 502 interceptor called _handleTokenExpiration(). | Server returns 502 | Retry message; stay logged in | Session cleared | Treat 502 as transient | lib\app\services\Network\network_module.dart | Fixed | 502 no longer calls _handleTokenExpiration(); shows retry message. | 5
QA-045 | Bug | Critical | Config | Default API points to dev tunnel | Fallback base URL was devtunnels.ms when .env missing. | Run without .env | Production API endpoint | Dev tunnel used | Default to production API URL | lib\app\services\Network\urls.dart; api_config.dart | Fixed | Default API URL set to production; ApiConstants.defaultBase = prod. | 1
QA-046 | Test Gap | Critical | Tests | Broken default widget test | Test imported wrong package and expected counter app. | Run flutter test | Passing smoke test | 0/1 compile failure | Fix test import and expectations | billkaro_windows\test\widget_test.dart | Fixed | billkaro_windows widget test replaced; 1/1 smoke test passes. | 1
QA-051 | Bug | High | Network | Connectivity check type mismatch | Compared List<ConnectivityResult> to ConnectivityResult.none. | Call hasInternetConnection() | Correct none-network detection | Wrong online/offline state | Use result.contains(none) | lib\utils\connectivity\connectivity_helper.dart | Fixed | NetworkUtils uses result.contains(ConnectivityResult.none). | 3
QA-052 | Test Gap | High | billkaro-app | Missing app_snackbar.dart breaks tests | billkaro-app missing utils/app_snackbar.dart. | Run flutter test in billkaro-app | All tests compile | 4 compile failures | Copy app_snackbar.dart from billkaro_windows | billkaro-app\lib\utils\app_snackbar.dart | Fixed | app_snackbar.dart copied to billkaro-app; compile errors resolved. | 4